## project-gantt-chart-o
Project Gantt Chart of Quantum Computation
This Gantt chart is for Cyber security capstone's course
MileStone 1 (Project Proposal)
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
Team formation ➡️ | Zexi Xing | Done | 2021-01-18 | 2021-01-20 | High
First Intenal team meeting |  | Done | 2021-01-21 | 2021-01-21 | Critical | Team formation ➡️
Second meeting with Dr.Hale |  | Done | 2021-01-26 | 2021-01-27 | Critical | Brainstorming topics
Second internal meeting |  | Done | 2021-01-29 | 2021-01-29 | Medium | Second meeting with Dr.Hale
Meeting with Client |  | Done | 2021-02-02 | 2021-02-02 | High | Second internal meeting
Working on QKD |  | Approved | 2021-02-03 | 2021-02-13 | Critical | Meeting with Client
Literature review document |  | Working on it | 2021-02-03 | 2021-02-10 | High | Meeting with Client
Resources Needed |  | Working on it | 2021-02-03 | 2021-02-11 | High | Meeting with Client
Submit Project Proposal |  | To do | 2021-02-12 | 2021-02-12 | Critical | Literature review document
|  |  | 2021-01-18 | 2021-02-13
Milestone 2 (Prototype Deliverable and Paper outline)
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
Starting point ➡️ |  | To do | 2021-02-15 | 2021-02-19 | Medium | Submit Project Proposal
Working forward |  | To do | 2021-02-22 | 2021-03-11 | High | Starting point ➡️
Problem solving |  | To do | 2021-03-11 | 2021-03-26 | Important | Working forward
Client Meeting |  | Ready for review | 2021-03-27 | 2021-03-27 | High | Problem solving
Internal Meeting |  | Ready for review | 2021-03-28 | 2021-03-28 | Medium | Client Meeting
Prototype Deliverable submission |  | To do | 2021-03-29 | 2021-04-02 | Critical | Internal Meeting
|  |  | 2021-02-15 | 2021-04-02
Milestone 3 (Final Deliverable and Research Paper)
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
Starting Point ➡️ |  | To do | 2021-04-05 | 2021-04-09 | Low | Prototype Deliverable submission
Working Hardly |  | To do | 2021-04-12 | 2021-04-16 | High | Starting Point ➡️
Refining process |  | To do | 2021-04-19 | 2021-04-23 | Important | Working Hardly
Client Final CheckPoint |  | Ready for review | 2021-04-24 | 2021-04-24 | Critical | Refining process
Internal Final Revise |  | Ready for review | 2021-04-25 | 2021-04-25 | Critical | Client Final CheckPoint
Final Deliverable and Research Paper sumission |  | To do | 2021-04-26 | 2021-05-05 | Important | Internal Final Revise
|  |  | 2021-04-05 | 2021-05-05