## Task Timeline
Board - Project Gantt Chart of Quantum Computation (by years)
|  |  | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023
| Start | End | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
group - MileStone 1 (Project Proposal) |  |  | Jan: group - MileStone 1 (Project Proposal)
Team formation ➡️ | 18-Jan-2021 | 20-Jan-2021 | Jan: Team formation ➡️ (18-Jan-21 - 20-Jan-21)
First Intenal team meeting | 21-Jan-2021 | 21-Jan-2021 | Jan: First Intenal team meeting (21-Jan-21 - 21-Jan-21)
Second meeting with Dr.Hale | 26-Jan-2021 | 27-Jan-2021 | Jan: Second meeting with Dr.Hale (26-Jan-21 - 27-Jan-21)
Second internal meeting | 29-Jan-2021 | 29-Jan-2021 | Jan: Second internal meeting (29-Jan-21 - 29-Jan-21)
Meeting with Client | 02-Feb-2021 | 02-Feb-2021 | Feb: Meeting with Client (02-Feb-21 - 02-Feb-21)
Working on QKD | 03-Feb-2021 | 13-Feb-2021 | Feb: Working on QKD (03-Feb-21 - 13-Feb-21)
Literature review document | 03-Feb-2021 | 10-Feb-2021 | Feb: Literature review document (03-Feb-21 - 10-Feb-21)
Resources Needed | 03-Feb-2021 | 11-Feb-2021 | Feb: Resources Needed (03-Feb-21 - 11-Feb-21)
Submit Project Proposal | 12-Feb-2021 | 12-Feb-2021 | Feb: Submit Project Proposal (12-Feb-21 - 12-Feb-21)
group - Milestone 2 (Prototype Deliverable and Paper outline) |  |  | Jan: group - Milestone 2 (Prototype Deliverable and Paper outline)
Starting point ➡️ | 15-Feb-2021 | 19-Feb-2021 | Feb: Starting point ➡️ (15-Feb-21 - 19-Feb-21)
Working forward | 22-Feb-2021 | 11-Mar-2021 | Feb: Working forward (22-Feb-21 - 11-Mar-21); Mar: Working forward (22-Feb-21 - 11-Mar-21)
Problem solving | 11-Mar-2021 | 26-Mar-2021 | Mar: Problem solving (11-Mar-21 - 26-Mar-21)
Client Meeting | 27-Mar-2021 | 27-Mar-2021 | Mar: Client Meeting (27-Mar-21 - 27-Mar-21)
Internal Meeting | 28-Mar-2021 | 28-Mar-2021 | Mar: Internal Meeting (28-Mar-21 - 28-Mar-21)
Prototype Deliverable submission | 29-Mar-2021 | 02-Apr-2021 | Mar: Prototype Deliverable submission (29-Mar-21 - 02-Apr-21); Apr: Prototype Deliverable submission (29-Mar-21 - 02-Apr-21)
group - Milestone 3 (Final Deliverable and Research Paper) |  |  | Jan: group - Milestone 3 (Final Deliverable and Research Paper)
Starting Point ➡️ | 05-Apr-2021 | 09-Apr-2021 | Apr: Starting Point ➡️ (05-Apr-21 - 09-Apr-21)
Working Hardly | 12-Apr-2021 | 16-Apr-2021 | Apr: Working Hardly (12-Apr-21 - 16-Apr-21)
Refining process | 19-Apr-2021 | 23-Apr-2021 | Apr: Refining process (19-Apr-21 - 23-Apr-21)
Client Final CheckPoint | 24-Apr-2021 | 24-Apr-2021 | Apr: Client Final CheckPoint (24-Apr-21 - 24-Apr-21)
Internal Final Revise | 25-Apr-2021 | 25-Apr-2021 | Apr: Internal Final Revise (25-Apr-21 - 25-Apr-21)
Final Deliverable and Research Paper sumission | 26-Apr-2021 | 05-May-2021 | Apr: Final Deliverable and Research Paper sumission (26-Apr-21 - 05-May-21); May: Final Deliverable and Research Paper sumission (26-Apr-21 - 05-May-21)